## Agile Project Plan
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
| Gaming hale system | GHANEM DARBOULI | 2020-06-09 | 2020-09-09 |  | 20% |  | SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
| Sprint 1 : SRS FOR PROJECT |  | GHANEM DARBOULI |  | 2020-06-09 | 2020-07-08 | 29 | Complete
| COLECTE REQUREMENTS |  | ZEINA ALSHAMAA |  | 2020-06-09 | 2020-06-19 | 10 | Complete
| DESIGNE UML DIGRAM |  | AHMAD AHMAD |  | 2020-06-19 | 2020-06-30 | 11 | Complete
| CREATE SRS DOCUMENTION |  | ALI KASSEM |  | 2020-07-01 | 2020-07-10 | 9 | Overdue | ALI LATE ONE DAY TO FINISH THE SRS.
| Sprint 2 : CREATE DATABASE |  | AHMAD AHMAD |  | 2020-07-11 | 2020-07-26 | 15 | In Progress
| CREATE TABLES |  | ZEINA ALSHAMAA |  | 2020-07-11 | 2020-07-16 | 5 | Complete
| REALATIONSHAP |  | ALI KASSEM |  | 2020-07-17 | 2020-07-21 | 4 | In Progress
| FUNCTION AND PROCEDUER |  | GHANEM DARBOULI |  | 2020-07-22 | 2020-07-28 | 6 | Not Started
| Sprint 3 : DESIGNE GUI |  | ZEINA ALSHAMAA |  | 2020-07-29 | 2020-09-06 | 39 | Not Started
| DESIGNE IN PHOTOSHOP |  | GHANEM DARBOULI |  | 2020-07-29 | 2020-08-13 | 15 | Not Started
| CREATE ACTIVITY IN ANDROID |  | ALI KASSEM |  | 2020-08-14 | 2020-08-24 | 10 | Not Started
| GUI PROGRAMING |  | AHMAD AHMAD |  | 2020-08-25 | 2020-09-06 | 12 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET

## Agile Project Plan - BLANK
AGILE PROJECT PLAN TEMPLATE
| PROJECT NAME | PROJECT MANAGER | START DATE | END DATE |  | OVERALL PROGRESS |  | PROJECT DELIVERABLE
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DURATION (DAYS) | STATUS | COMMENTS
Sprint 1
Feature 1
Feature 2
Feature 3
Sprint 2
Feature 4
Feature 5
Feature 6
Sprint 3
Feature 7
Feature 8
Feature 9

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.